## Materials Supply Report
Materials Supply Report - 05 March 2021
Category | Sub-Category | Manufacturer | Country of Manufacture | Components Imported | Stockholding | Lead Times - Days | Lead Times - Additional Info | Risk Status | Risks to Note | Mitigation Strategies
Access Control Equipment |  | Pelco Limited | Taiwan for majority | Taiwan, China, Philippines | No increase in stockholding | No change |  | G | UK supplier will be treated as a foreign entity for its European business. Product purchased from the UK delivering to the US will have no process change, but product delivering to EU distribution center will need to be managed an import rather than as an intracommunity transfer. Business related to product from our UK supplier will also need to be adjusted to account for additional cost related to import processing.
Access Control Equipment |  | Capita Plc | USA China Taiwan |  | No increase in stockholding | No change |  | G | 90% of goods supplied are manufactured in East Asia and the USA Limited impact in the event of No Deal | We have conducted detailed contingency planning to assess the impact of leaving the EU on our operations and have worked across the business to understand and mitigate any risks. We believe that we are well prepared and we are supporting our colleagues, clients and partners throughout this process.
Access Control Equipment |  | Anixter | UK distributer | Commscope cabling - stock from european warehouse in holland, manufacture cable in ireland, US and middle east. Access Cameras made in europe and we would buy from axis uk with components made in US and Europe - pulled together in Sweden. | No increase in stockholding | No change |  | G | Aware of WTO potential duty implications across our product portfolio. Some are zero rated, others typically attract 2 – 8% with the majority of products at 2%. No clear position has been finalized on duty or pricing impact into 2021
Aggregates/Asphalt and Concrete | Concrete/Aggregates and Mortar | Cemex | UK | Ground Granulated Blast frunace Slag small % of total and Original Equipment Manufacturer spares. | Increased stock of plant equipment spares. No change post Brexit | 1 | No change. No delays due to Brexit - Worked through the whole pandemic efficiently. Overall neither Covid or Brexit have had a detrimental effect on our business | G | Some cost increases on products like steel/carbon but not direct costs to Asphalt and Aggregates. Carbon price will begin to have impact on Concrete costs going forward.
Aggregates/Asphalt and Concrete |  | Hanson | UK | None | Planned for winter stops by making sure parts were in stock. | 1 | Main Brexit impact is import of parts, we are planning for longer lead times but this is no affecting delivery. | G | No particular impact predicted. No change on stockholding or lead times or price due to Covid/Brexit.
Building Management Systems Field Equipment |  | UK Electric | Europe (85%) - notably Scandanavia |  | 10% increase in stock | 13 | We are seeing longer lead times than anticipated at the moment – manufacturers are quoting an extra 10 days at present but are also assuring us that this is a temporary situation, and should clear by the end of Q1. | A | Potential price increases of 1-2% on core items. No critical impact from tariffs. | Yes have a whole range of SPI's plus a Brexit statement. Buying from and selling to UK companies. Distribution could a risk a fuel shortage.This is only partially applicable to us as we may be affected indirectly.
Building Management Systems Field Equipment |  | Titan Products | UK China - tablet screens only | 1%. The vast majority of our build components are sourced from UK distribution. | 10% increase in stock | No change | No. Our contingencies and Stockholding is designed to mitigate increases in lead times on finished product. | A | Majority of component purchasing and supply of finished product is UK based Limited impact anticipated | Yes. The plan is geared around stock and supplier management to ensure we have access to all critical components to ensure lead time impact and price increases are kept at an absolute minimal.
Building Management Systems Panels & Field Equipment |  | Industrial Switchgear | UK | France and Germany | 25% increase in stock | 28 | 2-4 weeks on excisting lead times initially but will start to ease | A | Impact supply of parts by 5%. | Dependent on their suppliers and do not buy direct from Europe. May manage how they buy stock such as bonded stock or buy outright to avoid cost impact. Schneider clear lid boxes as an example. This has been done for other key items they see at risk. Could be 50% on key items. Maybe double up again by end of the year - start to buy bigger bulk. Steel boxes/cases are kept in this country by such as Schneider and are stocking up.
Building Management Systems Panels & Field Equipment |  | Integra | Germany France Sri Lanka |  | No increase in stockholding | No change | No change | A | Minimal impact to panels manufacture. | We do not believe we will be affected.
Building Management Systems Panels & Field Equipment |  | Combined Services Limited | England Taiwan Romania Sweden France The Czech Repulblic Bulgaria |  | No increase in stockholding | Unknown |  | A | Minimal impact as obtaining from UK suppliers. | Can share if required.
Boilers |  | Hoval Limited | Switzerland Germany | Lichtenstein (80%) - Trade Agreement already agreed with UK Government and Switzerland/Lichtenstein 2019 Germany (10%) | 33% increase in stock | 3 | Eexperiencing slight delays | G | we have had minor impacts at the beginning of the year due to the "panic" to find a lorry across Europe. This is getting better now | Yes we have internal plan regardless of the final outcome as we have reviewed various scenarios. . The plan will be completed once we leave and implemented immediately.
Boilers |  | Baxi Heating UK Limited | UK The Netherlands | UK (80%) EU (15%) Asia (5%) | 30% increase in stock | No change | No change to current lead times - Baxi have a dedicated Brexit project team who have been working to prepare the business for Brexit and mitigate and negative impact on the supply chain for the last two years. | G | Impact of a no deal or a WTO agreement unknown at present | Baxi have a dedicated Brexit project team who have been working to prepare the business for Brexit and mitigate and negative impact on the supply chain for the last two years. To ease the move through customs we have employed a freight forwarder to manage the customs process, increased our stocks to help buffer a potential delay at customs, preparation of our internal systems to ensure complete and accurate data is available for increased customs checks, and are worked closely with our suppliers to ensure they are set up for Brexit. The Brexit team have also been covering all other aspects of the transition including, Trade marks, CA Mark, IP, EORI number, the transfer of data, VAT, Customs requirements, company law, insurance, consumer rights, product certifications, consumer protection, immigration rules, agency staff provision, EU nationals employed by Baxi in the UK. We have provisions in place to make sure we are where we need to be with each aspect to remove any risks bought on by Brexit.
Boilers |  | Tier 1 Boiler Manufacturer | France Germany Italy | China and Various EU countries | 50% increase in stock | Unknown | Where we are seeing delays in our category of products moving across borders it is largely down to groupage loads where one party on the vehicle has not correctly completed their paperwork; | G | There seems to be a lack of understanding of transit requiring permits which is further leading to increased costs | Increases in inventory. Resourcing products to UK where possible and practical.
Boliers |  | Hamworthy Heating | UK France | EU China India | 40% increase in stock | Unknown | Additional stockholding | G | Expect cost of transport to increase but no estimation at this point
Bricks & Blocks | Bricks | Ibstock | UK (99.5%) | Small amount of chemicals, adhesives and Original Equipment Manufacturer spares. | 6 months increased Stockholding | 28 |  |  | No impact on cost or supply
Bricks & Blocks | Blocks | Aggregate Industries | UK | None | Increase stock due to general demand (not Brexit related) | Unknown |  | G | No impact on cost or supply
Bricks & Blocks | Bricks | Weinerberger | UK, Austria, Belgium, Holland, Germany, Poland, Estonia, Denmark, France, America, Sweden, Finland, Norway, Latvia, Lithuania, Romania, Bulgaria, Hungary, Slovakia, Croatia, Bosnia and Herzegovinian, North Macedonia and the Czech Republic. |  | 3-6 months Stockholding at 6 UK ports. Each port carries around 5 million bricks from high volume product to specialist material 2 week turnaround – slightly increased stock on A & B rated products. | Unknown |  | G | No Brexit or Covid impact on supply just usual seasonal supply and demand issues
Busbar |  | E&I Engineering Ltd | Northern Ireland Ireland UAE USA | France, Italy, Netherlands and Germany | 30% increase in stock | 2 | Increase on current lead times | G | We are still able to import raw materials without tariffs from EU into NI due to the NI protocol. | We will manufacture in NI to serve the UK market. There will be no entry declarations and no tariffs for goods moving from NI to UK.
Busbar |  | Prism Power | Italy Germany |  | No increase in stockholding | No change | No expected delay to current lead times | G | Impact primarily sits with export work, not UK customer base.
Busbar |  | Elbagate Limited | Turkey |  | No increase in stockholding | No change | No impact. | G
Ceilings |  | Armstrong | UK | 86% UK but some raw material from EU | Increased contingency stocks | Unknown |  | G | Expect a delay at ports. | Armstrong recommend you provision for contigency stock and place orders ahead of year end.
Central Battery Equipment |  | Ventilux Limited | UK Ireland Turkey China | Ireland, Turkey, China, Taiwan, India and Germany | 22.5% increase in stock | 7 | Further 2 day Increase post Brexit on lead times | A | Goods imported into UK from Ireland and Germany although not subject to import tarriffs are subject to additional paperwork and small port delays due to custom checking. | No change in Labour/Increase stocks of finished goods /logistics, duty and finance mitigated
Central Battery Equipment |  | Power Control | Italy Portugal China |  | 20% increase in stock | 14 | Increase on current lead times | A | Currently import some product direct from China so have experience of this. | Increase Stockholding of commonly used product and spares for emergency repairs. Communicate lead times at proposal stage for none urgent installations.
Central Battery Equipment |  | Eaton Electrical Systems Limited | Germany | Poland, France and Germany | No increase in stockholding | Unknown |  | A | Impact mainly on delays and duty.
Chillers |  | Daikin Applied (UK) Limited | Italy | Italy and Germany | 10% increase in stock | No change |  | G | Possible duty. | Global operarion with many options to mitigate any negative impact.
Chillers |  | Airedale International Air Conditioning Ltd |  | Italy, France, Germany & USA | 30% increase in stock | No change | During weeks 1 &2 we experienced a lot of problems and major congestion at the ports. Transport operators werent accepting new orders. Situation now easing in week 5 | G | Had exected shipping costs to increase by 10% in actual fact it is 15-20%. Anticipate shipping delays to resolve in 2- 3 months. | Increased stock holding is not extending lead times
Chillers |  | Toshiba Carrier UK Limited | France Spain | All manufacturing is in EU. Only servicing, commissioning and spares are keep in UK. All raw materials come from France or Spain. | 25% increase in stock | 42 |  | G | 2.7% price increase forecast. However no current increase as a direct result of Covid or Brexit. We are experiencing minor disruption on the movement of goods although this is related to haulage red tape more than anything else
Combined Heat & Power Systems |  | Baxi Heating UK Limited | UK The Netherlands | UK - 80%, EU 15%, Asia - 5% | 30% increase in stock | No change | No - Baxi have a dedicated Brexit project team who have been working to prepare the business for Brexit and mitigate and negative impact on the supply chain for the last two years. | G | Impact of a no deal or a WTO agreement unknown at present | Baxi have a dedicated Brexit project team who have been working to prepare the business for Brexit and mitigate and negative impact on the supply chain for the last two years. To ease the move through customs we have employed a freight forwarder to manage the customs process, increased our stocks to help buffer a potential delay at customs, preparation of our internal systems to ensure complete and accurate data is available for increased customs checks, and are worked closely with our suppliers to ensure they are set up for Brexit. The Brexit team have also been covering all other aspects of the transition including, Trade marks, CA Mark, IP, EORI number, the transfer of data, VAT, Customs requirements, company law, insurance, consumer rights, product certifications, consumer protection, immigration rules, agency staff provision, EU nationals employed by Baxi in the UK. We have provisions in place to make sure we are where we need to be with each aspect to remove any risks bought on by Brexit.
Combined Heat & Power Systems |  | Hoval Limited | Germany Switzerland | Lichtenstein (80%) - Trade Agreement already agreed with UK Government and Switzerland/Lichtenstein 2019, Germany 10% | 20% increase in stock | 3 | Sl;ight increase | G | Trade Agreement already agreed with UK Government and Switzerland/Lichtenstein. Minor impact to lead times at the beginning of the year but getting better. | Increased Stockholding - measured against historical orders and current market forecasts. Spares/Materials +3 months stock.
Combined Heat & Power Systems |  | Centrica Business Solutions UK Limited |  | Canada, US, and China | 25% increase in stock | No change |  | G | No impact. | Additional stock levels in the Manchester factory.
Data Hub Equipment |  | Mayflex | UK |  | No increase in stockholding | 14 | Increase on current lead times post Brexit | A | Initially predicted a few days delay but now quoting 2 weeks | Work with your suppliers to manage deliveries and lead in times for the first quarter of the year.
Data Hub Equipment |  | Leviton (Brand Rex) | UK |  | No increase in stockholding | No change |  | A | Will absorb the impact.
Data Hub Equipment |  | Abtec | US Nordic countries including Norway |  | No increase in stockholding | No change |  | A | Minimal impact majority of equipment from US
Data Hub Equipment |  | Aruba | Multiple |  | No increase in stockholding | Unknown | Expect longer delivery times | A | Expect delays with customs clearance. | Urging customers to plan ahead and factor in increased lead times
Drainage | Plastic | Polypipe | UK | Some components from Europe | 4 weeks stock in the UK | No change |  | G
Drainage | Concrete/clay | Naylor | UK | None | Good levels of stockholding | Unknown |  | G
Ductwork (sub-contract) |  | E&S Heating & Ventilation Ltd | UK | Italy, Denmark, Sweden, Germany | 15% increase in stock | 14 |  | G | Significant cost increase to raw materials. | Early procurement of materials, holding additional stock where possible, manufacture ahead of programme
Ductwork (sub-contract) |  | ASM Ltd | UK | Italy and Romania | 100% increase in stock | No change |  | G | Increased in cost of raw materials anticipated | Significant increase in stock of raw materials.
Ductwork (sub-contract) |  | Gardner & Co Ltd | Netherlands |  | 10% increase in stock | No change |  | G | No Impact | We are sourcing UK manufacturers for our equipment.
Electrical Containment (basket, trunking, tray & ladder) |  | Legrand | France | China and India | 10% increase in stock | 5 | Increase on current lead times | G | Duty impact and delays at port. | Working with SUP to find alternative entry points
Electrical Containment (basket, trunking, tray & ladder) |  | Atkore - Unistrut | Belgium China Australia Russia New Zealand | China, India, Germany, Italy and Belgium | 10% increase in stock | No change |  | G | Possible duty risk. | Extra 10% warehousing, additional stock in place, back up machinery and tooling and equipment for continuity of supply.
External Doors | Revolving Doors | Quest | UK | All UK | No increase in stockholding | 56 | Current lead time 6-8 week | G | N/A | N/A
External Doors | Revolving Doors | Boon Edam | NL |  | Increased inventory of spare parts but all bespoke so no product stock. | 140 | Current lead time 16-20 weeks | G | Expect extended lead times. | They have built the extended lead time into customer quotes from July.
External Luminaires (all sectors) |  | LUG Light Factory Ltd | Poland |  | No increase in stockholding | 3 | Extended delays by a couple of days Due to additional paperwork, but would expect this to be a short term issue that would be recovered. | A | Current understanding is that a tariff of 2% will be applied to imports of lighting products from EU. This tariff will be the responsibility of the importing entity as part of the customs clearance process. | LUG are a project oriented business means that we can focus on the needs of individual projects and adjust production and delivery plans as necessary, to mitigate any challenges and ensure that client needs are met.
External Luminaires (all sectors) |  | Kingfisher | China Europe UK |  | No increase in stockholding | 10 | Increase on current lead times post Brexit | A | We are aware of import tax implications. | Our supplier base is China, Europe and UK. Products are similar but different price points. All can offer alternative options for our goods
External Luminaires (all sectors) |  | DW Windsor | UK | Spain, Germany, China, Italy and Finland are the main suppling non-UK countries. | 10% increase in stock | 28 | Increase on current lead times | A | Increase in import tariff anticipated Increase in lead times. | In summary we are arranging the following: • Increased stock levels • Close relationship with dedicated importer and clearance agent, • EORI and TSP numbers, ensuring we have commodity codes established, • Customs deferment account set up with sufficient funds.
Facades |  | Reynear | Europe (stocked in the UK) | Europe | Carrying 4 weeks of stock | 22 | For standard colours, 3 week lead time currently | G | Working with customers to manage lead time expectations as customer base demand on a buy to order basis. Currency risk assessed as minimal as taken hit. General lead times increased by 1.5 days post Brexit | Still carrying 4 week buffer stock
Facades |  | Metal Technology | Northern Ireland | Use Hydro for profiles. | Stockholding increased by 35% | 28 | Lead time on mill finished products 5 days. PPC Products currently 3-4 weeks but view will increase | G | Some delays are being experienced but not at a level that is impacting business. No significant cost increasses due to Brexit or Covid | Decision taken to extend increased levels of stock to the end of qtr 2 as a precaution
Facades |  | Kawneer | UK | Hardware from Mainland Europe | Over past 18 months Kawneer have been reviewing stock profiles. The net result is an investment in increased stocks for the fast moving products. Kawneer estimates they have increased stockholding by circa 65% ahead of Brexit. | 42 | Lead time 3 weeks standard 6 weeks non standard | G | Delay of 2- 3 weeks for Hardware. Expect this to continue into Early April. | Work with manufacturers early to secure up to date lead times
Facades |  | Senior Aluminium Systems | UK | Use Hydro for profiles and hardware and other components Europe | 5.5m-6m of stock and increased Polyamide strips Stockholding | 42 | Lead times Mill finished products 1 week. Powder coated profiles 3-4 weeks. Dual powder coated 5-6 weeks and pure profiles 5-6 weeks | G | Customs paperwork only delay. Circa a week extra delay. Commodity pricing on increase globally. Alluminium being the main concern. No pass on of price increases yet but being closely monitored. | Work with your fabricators and manufacturers early to have a clear agreed de livery schedule. Question any increases in estimating rates. Stockholding for extruders being kept to mitigate the extra lead time
Facades |  | Hydro Building Systems | UK Belgium - above 9" die capacity | Billet is from Norway. Thermal Break Switzerland and Norway. Hardware is from Europe. | 20% increase in stock of component items | 42 | Lead times 1-4 weeks standard PPC and 4-6 weeks for non standard PPC | G | No update. Risk that costs will increase with Tariffs, currency fluctuation and transport costs. Cannot yet forecast how much will be absorbed or passed on. Also been informed Freight companies unwilling to take risk on port delays. Onshoring exercise for recycled Billet could have some cost. | Work with your supply chain early and understand wether your manufacturer has freight capability inhouse
Facades |  | Heuck | Germany | Aluminium sources from EU countries, Australia and India. Thermal breaks from Germany, France and Italy. | No increase in UK but will look to get warehousing in UK as a last resort. | 56 | Current lead times 3-4 weeks for standard RAL and 4-6 weeks non standard. If no deal add 2 weeks onto both. | G | No update Early orders requested Anticipated port delays | Work with your fabricators and manufacturers early to have a clear agreed delivery schedule. Question any increases in estimating rates.
Facades |  | Skonto plan | Latvia | Glass, Aluminium,cladding panels and insulation sourced from mainland Europe, Turkey and UAE. | No Stockholding in the UK but access to warehouse storage facility for early delivery. | 364 | 11-12 months design to delivery | G | Some unitised elements 2 % tariff other components 3-4% tariff. Lead times extended and delays expected. | Facility to bring in earlier. Work with manufacturer to avoid delays.
Facades | Curtain Walling | Fochhi | Italy | 100% Europe | No Stockholding in the UK | 365 | 12 month lead time from Design to delivery on site | G | No update. No deal tarrif will be passed to customer and currency fluctuations will consistantly have an impact on pound vs euro. | Extended lead times for delivery built into proposals. However would monitor deliveries in the first quarter directly with manufacturer.
Fan Coil Units |  | TEV Ltd | Italy | Italy, China, Taiwan and Turkey | 10% increase in stock | 1 | Increase on current lead times | G | Increase in cost of raw materials anticipated | Not yet, subject to finalisation
Fan Coil Units |  | Ability Projects Ltd | UK | Germany, Switzerland, Turkey, Canada and Slovenia | 30% increase in stock | No change |  | G
Fan Coil Units |  | Diffusion Environmental Ltd | Germany | Germany | 40% increase in stock | Unknown |  | G | Tariff increase | An exercise is currently being carried out and we have increased our stock levels.
Foundation Steel Pipes |  | Arcelor Mittal | Europe |  |  | Unknown |  | A | For foundation pipes required for combined walls, there is currently a quota in place commencing January 2021 of ca 17kt per quarter for imports from the EU which, bearing in mind we may secure +/-5000-8000t per annum on UK projects in a normal year, should be an acceptable level. Any imports over the quota will incure a tariff. | Work with your supply chain to manage any risk by giving good demand and forecasting. Also work with your supply chain early to avoid problems in early project estimations that might not take into account tarriffs.
Foundation Steel Products |  | Arcelor Mittal | Europe |  |  | Unknown | Covers Z/U Pile, HZ-M system and cold formed ranges | A | No safeguard measures in place for hot rolled sheet piles from Europe into the UK.
Generators |  | Shenton Group | Czech Republic Italy Spain | Czech Republic, Italy and Spain | 15% increase in stock | 28 |  | G | Assessed all associated codes, no particular concern on tariffs, forecasted minimal impact if any.
Generators |  | TGC International Limited | Germany Italy Spain Ireland | Germany, Italy, Spain, Ireland | 50% increase in stock | No change | Not seen an increase in lead time | G | Marginal increase of 0.05% on transport cost only | Yes.
Generators |  | Advanced Diesel Engineering Limited | India Sweden | Sweden | 20% increase in stock | No change |  | G | Small generators are already covered by WTO Terms. | We have a plan in place as per the ISO9001 2015 requirements.
Generators |  | AVK | Germany UK Spain USA France |  | 20% increase in stock | No change |  | G |  | Stockholding mitigating any delays
Grilles & Diffusers |  | Waterloo Air Products Ltd | Holland Italy Sweden India | Holland, Italy, Sweden and India | 10% increase in stock | 7 | Increase on current lead times | G | Increase in raw material costs anticipated | Significant stock of raw materials backed up by ring fenced reserves held within their supply chain.
Grilles & Diffusers |  | Swegon | Spain | We do not manufacture in the UK. Our manufacturing base is in Spain. | 20% increase in stock | 7 | Increase on current lead times | G |  | Increase in stock level and early ordering.
Grilles & Diffusers |  | Gilberts of Blackpool Ltd | UK | China | 20% increase in stock | No change |  | G | None
Insulation |  | Kingspan | UK | Chemicals and Facers from the EU and America. | 1.5 weeks additional Stockholding. | Unknown | increase in lead time post brexit | G | No significant price increases and price increases already published
Insulation |  | Ecophon | Sweden France Poland |  | Increased UK saftey stock levels. | no change if in stock 2 weeks if not in stock | If not in stock lead time of 2 weeks | G | No significant price increases however nominal inflationary price increases on tiles | Built contigency stock.
Internal Doors |  | David Smith | UK | Majority of components from Europe, America and China | Increased Stockholding and also placing material orders prior to order approval | 40 | Design 7-10 days and manufacture 25-30 days | G | Expect future increase currently experiencing increase in hardwood and other raw materials
Internal Doors | Doorsets | Lloyd Worall | Denmark (90% UK (10%) | Ironmongery 20% EU | No Stockholding in the UK | 49 | Design and schedules 1 week 5 weeks manufacture and 1 week delivery | G | No expected impact as they export to Norway and will be similar. Changed port of entry and currency fluctuations between Pound and Danish Kroner more stable. Increase in shipping by £20.00 for paperwork but will not be passing this cost on. No increase as part. No significant increases in 2021 pricing.
Internal Doors |  | CCN | UK | Components UAE, Estonia, France and Germany | 6 months stockholding | 56 | 2 week design and 3-6 weeks manufacture | G | No significant increase in cost
Internal Luminaires (all sectors) |  | Trilux Lighting Limited | Germany | Germany, Spain and Austria | 25% increase in stock | 3 | Increase on current lead times | G | This forms part of Trilux overall risk analysis. | Trilux have Increased warehouse capacity, Product availability, Local manufacturing
Internal Luminaires (all sectors) |  | SG Lighting Ltd | Norway Denmark |  | No increase in stockholding | 3 | Increase on current lead times | G
Internal Luminaires (all sectors) |  | Whitecroft Lighting Limited | Italy | 30% European suppliers, 20% East Asia suppliers | 10% increase in stock | 2 | Increase experienced on lead times | G | W/L estimate that additional tariffs on imported materials will have a direct and indirect cost impact that would result in a 2% price increase if we move to WTO terms. | • Questionnaires were issued to suppliers to understand how prepared they are for a ‘no deal’ Brexit scenario. • There were two questionnaires issued distinguishing UK and EU production based suppliers separately, with questions adjusted to reflect production location. • The responses enabled both an analytical and worded response to allow suppliers to be categorised by risk in regards to their ability to deal with a worst case Brexit scenario and disruption to the supply chain. Conclusion/Actions: • 93% of UK suppliers have robust plans in place to protect the supply chain by significantly increasing their stock or ensuring that their supply chain has increased their stock. • EU suppliers that have a sales presence in the UK have proactively put plans in place to increase localised UK storage or have agreed to temporarily increase consignment stock levels where applicable • 25% of EU suppliers have put no plans in place. Actions taken • High risk suppliers: • Detailed analysis identified risk suppliers and stock has been increased of the critical parts • Consignments stocks have been increased where applicable • Closer dialogue with our forwarding agent
Integrated Plumbing Systems & Washrooms (sub-contract) |  | C&B Systems Limited | Germany |  | 10% increase in stock | 70 | Increase on current lead times | G | Concerns about stage tariffs. | All current contracts have had supply orders placed and delivery dates agreed. When dates could not be confirmed C&B Systems have taken kit early and have placed it in stock. We have taken additional industrial units to cover storage. We have advised clients of any expected impact for new project for 2021.
Ironmongery |  | Lloyd Worrall | UK | 20% manufactured in the EU | Increased Stockholding for core range to 6 months and those manufactured in Europe we are holding 12 months | 2 |  | G | No expected impact unless significant currency fluctuation. | They have built up 12 months EU stock and moved ports 12 months ago to a quieter less busy port
Joinery |  | Essexford Joinery | Ireland | Timber sourced North America and additional suppliers in Europe. | 50% excess stock and extra warehousing in the UK. | 56 | 6-8 weeks | G | Hedge currency so no impact and don’t use Kent ports.
Lifts (passenger & goods) |  | Orona | Spain | 99% imported | £2m parts held in UK and delivering earlier into the UK and storing | 126 | 4 week design, 2 week apporoval and 12 week manufacture | G | Current prediction is a 5% increase in cost due to Brexit. | Fixed price at tender but future extimation would need to be revised.
Lifts (passenger & goods) |  | Schindler | Europe | Slovakia, switzerland and Italy | Will monitor situation and can bring to the UK early and store | 210 | 8 weeks design and 22 weeks manufacture | G | Current prediction 10% increase in material pricing
Lifts (passenger & goods) |  | Kone | Finland Italy Europe China - Escalators |  | 3 months stock of consumable parts replenishment strategy on "bespoke" components Strategy of advanced deliveries with storage facility at Alconbury for capacity of approx 450 lifts (typical deliveries in month 110-125). | 238 | 2-8 weeks design, 16-26 weeks manufacture. Accelerated options for standard at 10 weeks. | G | Not experiencing delays
Lighting Control Equipment |  | IBT Group | Germany France China | Germany, France and China | 10% increase in stock | 14 | Increase on current lead times post Brexit | A | Previously stated days increase on lead time now 2 weeks. | Improved processes to enable closer tracking of potential orders and forward lead times of products.
Lighting Control Equipment |  | Simmtronic Limited | UK | Finland, Japan, China, Korea, US and Canada | 50% increase in stock | N/A | N/A | A | None | Simmtronic plan well in advance for all their components, so they have planned a large order of components, enough to cover 3 years’ worth of production based on average build quantities. Due to Covid what they planned is lasting longer as shipping slowed, but they are committed to stock hence the large current stock levels. Even with the supply from Finland. They buy plugs and sockets direct from Ensto in Europe, they hold large stocks. But they also have UK distributors if they ever need to use them, which they never have to date due to the amount they hold in stock.
Lighting Control Equipment |  | Zen Control | China | China | 10% increase in stock | No change |  | A | Minimal impact at this stage.
Low Voltage Switchgear |  | E&I Engineering Ltd | Northern Ireland Ireland UAE USA | France, Italy, Netherlands and Germany | 30% increase in stock | 2 | Increase on current lead times | G | We are still able to import raw materials without tariffs from EU into NI due to the NI protocol. | We will manufacture in NI to serve the UK market. There will be no entry declarations and no tariffs for goods moving from NI to UK.
Low Voltage Switchgear |  | Prism Power | Italy Germany |  | No increase in stockholding | No change |  | G | Impact primarily sits with export work, not our UK customer base.
Low Voltage Switchgear |  | Armah Switchgear | UK | France and Italy (Tx) | No increase in stockholding | No change |  | G | Can not foresee any impact on items specific to current product profile. | Full Brexit statement provided to CHt, forecasted minimal impact.
Mechanical Services
Mechanical Ventilation with Heat Recovery |  | Systemair MVHR | Lithuania Germany Sweden | Lithuania, Germany and Sweden | 20% increase in stock | 1 | Increase on current lead times | G |  | Increased stock levels and early ordering
Mechanical Ventilation with Heat Recovery |  | Vent Axia ltd | Germany | Germany | 60% increase in stock | No change | Increased stock holding | G | 1.5% tariff | Currently ongoing.
Mechanical Ventilation with Heat Recovery |  | Elta | Germany Italy China Spain | Italy, Germany and China | No increase in stockholding | Unknown |  | G | Possible increase in material costs. | We are manufacturing as much as we can in the UK and have audited our supply chain and are satisfied with their increased stock levels.
Paint |  | Akzonobel | UK | 20% pigments and resins. | Stock levels are increasing post covid | No change | No change to lead times but any large volumes must have a minimum of 2 weeks | G | Expecting a 6% increase in price Large volume or specials will need a longer lead time.
Paint |  | PPG | UK | Pigments and resins |  | 14 days | large volumes 2 weeks notice | G | Published 5% list price increase
Photo Voltaic (sub-contract) |  | Photon Energy Ltd | China Germany |  | No increase in stockholding | 7 | Potentially by 1 week due to port delays. | G |  | The main issue that they see may come is the exchange rate changing so they have plans in place to hedge.
Photo Voltaic (sub-contract) |  | Spirit Energy | Europe - Germany, Holland, Slovenia Asia - Taiwan, S. Korea, Vietnam and Malaysia |  | No increase in stockholding | 21 |  | G | Import duties applied to goods are likely to increase.
Photo Voltaic (sub-contract) |  | Solstice Energy | China Mexico Philippines The Netherlands | China, Mexico, Philippines and The Netherlands | No increase in stockholding | Unknown |  | G | No impact.
Plasterboard |  | Knauf | UK Europe East Asia | Some accessory products fixings and finishings EU France and Germany | 6 weeks increase in UK stock | 8 |  | G | Have own ports so do not perceive issues however do think driver availability could be a problem also due to covid.
Plasterboard |  | British Gypsum | UK | Accessories and some boards, Habitat, Glasroc, Rigider(ceilings) | Increased stockholding where assessed as high risk Maximum capacity in wharehouses wherever possible | N/A | N/A | G | Not expecting significant increases in transport and duty costs but currency is a real risk but this is too uncertain to predict.
Plasterboard |  | Siniat | UK | Promat, compounds, screws and some metal and plasterboard from Mainland Europe and China. | They have been told by their customs expert to expect delays in the first week of January. Built stock levels up in December so they do not have to import in January. | Unknown | Fluctuating lead times due to fall out of covid | G | Expect impact if no deal on import tax, duties and transport costs. | Advise is to work with your manufacturers to give them good sight of demand over the next 6-9 months.
Plate Heat Exchangers |  | McCallum Water heating | Expansion Vessels and Immersion heaters - Italy Pumps- Germany Valves- most likely China Gas fired water heaters - USA | Nearly all materials are bought from Uk suppliers however materials like Mild Steel, Copper and stainless steel sheet along with Flanges and fittings nearly all originate from China, Plate heat exchangers parts are (regardless of manufacturer) all from mainland Europe and assembled in the UK. | 30% increase in stock | No change |  | G | Watching steel and copper prices due to Covid shortage
Plate Heat Exchangers |  | HRS Hevac Ltd | Italy Germany China | China, Italy, Poland and Germany | 20% increase in stock | Unknown |  | G | Minimal impact as HRS do not import. We source EU manufactured components via UK supply chain. | Increased stock holding minimising any risks
Plate Heat Exchangers |  | Ormandy Group | UK | Valves - China & Germany Raw materials - Poland, Germany and Italy | 20% increase in stock | Unknown |  | G | Minimal impact due to most bespoke equipment is built and sold in the UK. | Duel sourcing between EU & UK to ensure we mitigate risk during transition. Spare components increased at Bradford factory & increased ability to supply alternative components made in UK.
Pumps, Press Units & Booster Sets |  | Wilo (UK) Limited | France Germany | France, Germany, Italy and Spain | 20% increase in stock | 28 | Increase on current lead times post Brexit by an extra 2 weeks | A | 1.7% to 8% tarriff depending on Commodity. | Have adequate storage already with spare capacity Have increased stock by 20%
Pumps, Press Units & Booster Sets |  | Grundfos Pumps Limited | Denmark Hungary China | Denmark | 100% increase in stock | Unknown |  | A | Tariff increase | Working on.
Pumps, Press Units & Booster Sets |  | Armstrong Integrated Limited | UK | India, America, China and Europe | 10% increase in stock | Unknown |  | A | Possible increased costs associated with tariffs. | Have weekly senior team meetings on Brexit with both UK and Canadian Directors.
Raised Access Floors |  | Kingspan | UK | Steel and chipboard from EU and pedestals outside EU. | Increased stock of imported components | 42 | Current 4-6 week lead time | G | Expect currency fluctuations to affect price and a direct 6.5% increase in price if No deal.
Rebar |  | Hyten | UK | UK Celsa and Europe | Good levels of stockholding | 4 | For material in stock, our lead-time from order placement is about 3-4 days. For material not in stock, that needs to be produced it goes from 3-4 days to 5 weeks maximum. | A | UK mill has the capacity to supply our UK customers and any potential increase in the demand that could arise due to Brexit. The rebar price is currently volatile and is directly related to our main raw material costs, especially the scrap. Therefore, changes in the scrap have a direct and fast impact on rebar price. | Work with your supply chain to manage any risk by giving good demand and forecasting. Ensure you engage early to determine correct pricing.
Roof Tiles | Concrete/clay | Marley | UK | 99% Uk but timber from Sweden | Increased where possible timber stocks | 112 | Average lead times are 14-16 weeks Plain tiles 10 weeks Concrete 14 weeks Timber Batons 16-20 weeks | G | timber batons have been affected, lead times increased and price increased 18% from September 2020
Roof Tiles |  | Weinerberger | UK,Austria, Belgium, Holland, Germany, Poland, Estonia, Denmark, France, America, Sweden, Finland, Norway, Latvia, Lithuania, Romania, Bulgaria, Hungary, Slovakia, Croatia, Bosnia and Herzegovinian, North Macedonia and the Czech Republic. |  | 3-6 months Stockholding at 6 UK ports. Each port carries around 5 million bricks from high volume product to specialist material 2 week turnaround – slightly increased stock on A & B rated products. | Unknown |  | G
Sanitaryware |  | Geberit | Europe |  | 6 weeks of fast moving items in the warehouse | 15 |  | A | Expect disruption to supply for short period of 2-4 weeks. Customs clearance costs already incorporated to 2021 5 % price increase. Increase of 3% above what was expected on transport
Sanitaryware | Sanitaryware | Kaldwei | Germany |  | Working on a plan to bring Jan 2021 orders into temporary warehousing in Dec2020 | 28 | 2-4 weeks lead times | A | Border delays in the first few weeks was more than expected by 2-3 weeks however this has dramatically improved and only experiencing 2-3 days delay Experiencing increase in logistics costs
Sanitaryware | Sanitaryware | V&B | Germany |  | £8.3m of stock in UK | 56 | Made to order 8 weeks. Call off from project stock 1 week | A | Price increases as normal accounting for customs and duty will be published Jan 2021 to commence April 2021.
Sanitaryware | Sanitaryware and brassware | Vitra | Turkey |  | Increase stock of fast moving items in the UK | 70 | Normal 8 weeks but currently 10 weeks | A | Issues with shortage of containers easing. Still experiencing customs clearance delays and agencies are suggesting driver shortages | Giving UK shipments priority in factory so can make up for any lost time at ports.
Sanitaryware (Core Commercial/healthcare ranges) |  | Duravit UK Limited | Germany France Egypt Turkey Tunisia China |  | 50% increase in stock | 14 | Increase on current lead times post Brexit | A |  | Increased Stockholding Amended packaging in line with new standards
Sanitaryware (Core Commercial/healthcare ranges) |  | CP Hart Limited | Italy Germany Middle East China |  | No increase in stockholding | 1 | Increase on current lead times | A | Increased costs anticipated | Increased Stockholding at CP Hart and the in Supply chain Agreements to fix prices into early 2021 for larger projects, price rises likely to affects smaller projects
Sanitaryware (Core Commercial/healthcare ranges) |  | Ideal Standard | France Germany Italy East Asia | 2/3 Italy and France, 1/3 China | No increase in stockholding | Unknown |  | A | International transport costs and ocean freight costs have increased significantly. European road haulage costs increased. List price increase from 1st May 2021. Large increase in Copper and MMA (ingrediant within Acrylic products. Increase 5% on all products within fittings. 10% shower enclosures and 5% bathing products | Mapping process flows for individual products to determine the optimum process to follow for each.
Sectional Cold Water Storage Tanks (inc sprinkler tanks) (sub-contract) |  | Nicholsons Plastics Limited | Republic of Ireland | Belgium, Thailand, Slovakia and Italy | 25% increase in stock | 28 | Increase on current lead times | G | Minimal impact as if need all material can be purchased in the UK.
Sectional Cold Water Storage Tanks (inc sprinkler tanks) (sub-contract) |  | Balmoral Tanks Limited | UK | Spain | 75% increase in stock | Unknown |  | G | Increased costs associated with tariffs these are still to be advised. | Supplier agreements in place.
Security & Fire Alarm (Sub-contract) |  | Honeywell MK | China Malaysia India | UK, Denmark, Germany, Hungary, Sweden.Vietnam, Taiwan, Hongkong, China and Malaysia | 8% increase in stock | 5 | Increase on current lead times | G | There is likely to be zero direct effect on material and goods sourced within the UK - This also includes a study of Tier 2 suppliers. For suppliers within the EU - overall the total impact is estimated to be 1.5% of our total spend driven by Tier 1 and Tier 2 EU or EU-FTA content. This is an 'across the board' figure - some may not be affected but others may have a greater impact. | we have many mitigation measures currently including pull forward of our monthly forecasting for raw materials, components, Buy to Sell and finished goods in order to mitigate the risk of potential delays, come the New Year, for cross border activity (UK to EU and EU to UK).
Security & Fire Alarm (Sub-contract) |  | Johnson Controls Ltd | UK | 5% - Worldwide due to number of components | No increase in stockholding | No change |  | G |  | Looking at additional storage options, Rail Vs Port, Currency monitoring FX rates Held for a year.
Security & Fire Alarm (Sub-contract) |  | Johnson Controls Limited | UK | Worldwide due to number of components. | No increase in stockholding | Unknown |  | G |  | Looking at additional storage options, Rail Vs Port, Currency monitoring FX rates held for a year.
Security & Fire Alarm (Sub-contract) |  | Protec Fire Detection Plc | UK | China, Malaysia, Japan, South Korea and Singapore | No increase in stockholding | Unknown |  | G | Limited impact anticipated | Increased component/sub-assembly stock levels for our EU partner companies and EU clients, which in turn will assist in mitigation for the UK market under "no-deal" scenario.
Soft & Hard Landscaping |  | Marshalls | UK | 2% imported stone from Vietnam, China, India and EU | 3 months Increased critical stock | 5 | Standard items 3-5 days | G | Tarriffs added to imports. | Changed from road transport to sea
Soft & Hard Landscaping |  | Tobermore | UK | Pigment from Europe | Stockpiled significant amounts | 56 | 4-8 weeks | G | No impact expected. | Don’t use Kent ports for import
Soft & Hard Landscaping |  | Brett | UK (95%) | Pigment banding and pallets from Spain, Germany, Austria, Italy, Latvia, China and Italy. | 3-4 month Stockholding of raw material. | 56 | Block paving 1-4 weeks Commercial up to 8 weeks Specials 6-7 weeks | G | No real impact expected. The problem is demand for product by HB and over covid shutdown has created a supply issue.
Soft & Hard Landscaping |  | Charcon | UK | Natural stone from China and Europe Pigment from EU | Will increase stock by the end of the year. | 112 | 6-8 weeks made to order and up to 16 weeks on natural stone | G | Expected duty impact if no deal. Ships intp felixstowe which is reporting a 2 week delay currently.
Sprinkler Pumps Sets & Dry Riser Equipment (sub-contract) |  | Hall and Kay | USA Turkey China India |  | No increase in stockholding | 28 | Increase on current lead times | G | Minimal impact using WTO terms for rest of the world.
Sprinkler Pumps Sets & Dry Riser Equipment (sub-contract) |  | Compco Fire Systems Limited | Eastern Europe |  | 50% increase in stock | Unknown |  | G | The supply chain is working out the HS codes to find out where their products sit. | Have conducted a full supply chain review focusing on additional costs, resiliance to border delays, staffing issues, solvency and wage thresholds.
Sprinkler Pumps Sets & Dry Riser Equipment (sub-contract) |  | Argus Fire Protection Company Limited |  | Turkey, USA, China, the Netherlands and Italy | No increase in stockholding | Unknown |  | G
Street Lighting |  | LUG Lighting UK Limited | Poland |  | No increase in stockholding | 2 | Due to additional paperwork, but we would expect this to be a short term issue that would soon be recovered. | A | Current understanding is that a tariff of 2% will be applied to imports of lighting products from EU. This tariff will be the responsibility of the importing entity as part of the customs clearance process. | LUG Lighting only move finished goods into the UK. They are project oriented business meaning that they can focus on the needs of individual projects and adjust delivery plans as necessary to ensure that customer needs are met. LUG do not have storage facilities in UK, as they are based only max 5 days away from UK market. They do however have the option to hold stock of critical goods at the premises of Value Addeed Partners, if this was essential or beneficial to mitigate any challenges and ensure that client needs are met.
Street Lighting |  | Kingfisher Lighting | China Europe UK |  | No increase in stockholding | 10 | Increase on current lead times post Brexit | A | They are aware of import tax implications. | Kingfisher supplier base is China, Europe and UK. Products are similar but different price points. All can offer alternative options for their goods.
Street Lighting |  | CU Phosco | UK | China 10%; Germany 30% | 10% increase in stock | 14 | Increase on current lead times | A |  | Have provided supporting document 'BREXIT STATEMENT SEPTEMBER 2020'
Steel |  | UK Steel | Multiple | Multiple | N/A | N/A | Teething issues of customs processes covid tests and lack of transport availability are improving | A | No product category has seen its import quotas exhausted except a portion of Large welded tubes 25A. All EU quotas open. Recovery in China has rallied prices by $300/t and reached 10 year highs Volatility will continue over next quarter
Structural Steel |  | Severfield | UK | Steel plate from EU | 3 months stock | 70 | Sections 6 weeks Hollow sections 10 weeks plate 10 weeks | A | No direct impact of Brexit on cost. Steel cost increased
Structural Steel | Gantries bridges | Victor Buyck | Belgium | Steel plates UK, Gemany,France Austria and Denmark | No increase Stockholding as project specific. | 112 | Project specific but average time for steel plate from mill to factory 3-4 months | A | Structural Steel costs increasing dramatically although cause not necessarily related to Brexit
Structural Steel | Bridges | Cleveland | UK | Minimal amount of steel plates not manufactured in the UK sourced from western Europe. | Good levels of raw material stock | Unknown |  | A | Structural steel cost soars
Supply & Extract Fans |  | Systemair Fans | Sweden Spain Germany Lithuania Slovakia |  | 20% increase in stock | 7 | Increase on current lead times | G |  | We have numerous factories across Europe serving the UK and EU. No single product is made in a single factory.
Supply & Extract Fans |  | Vent Axia Fans | Germany | Germany | 30% increase in stock | No change |  | G | 1.5% tariff | Risk Mitigation is currently underway.
Supply & Extract Fans |  | Elta Fans Ltd | Italy Germany China Spain | Italy, Germany and China | No increase in stockholding | No change |  | G | Possible increase in raw material costs. | We are manufacturing as much as possible in the UK and have liaised with our external supply chain who have increased their stock levels sufficiently.
Soil Vent Pipe Tube & fittings (High Density Polyethylene) |  | Geberit | Europe (90%) - France, Italy, German, Ukraine and Poland East Asia (10%) |  | 100% increase in stock | No change |  | G | Believe there will be disruption during January which will settle down and actually an overstock situation is expected. | Not shared.
Soil Vent Pipe Tube & fittings (Polyvinyl chloride) |  | Polypipe | Italy Spain | Holland and France | 25% increase in stock | No change |  | G |  | Forward Orders.
Thermal Insulation (sub-contract) |  | Excel 2002 Ltd | USA China Germany |  | No increase in stockholding | Unknown |  | G | A proportion of labour have decided to move back to originating country like Poland | Helping EU labour to transition to a settled status as our business is very reliant on EU labour.
Thermal Insulation (sub-contract) |  | Linear Insulation Limited | UK |  | 10% increase in stock | Unknown |  | G | No impact as don't directly source from EU. | Main risk is associated with labour as high volume of UK thermal insulators come from outside UK. Poland & Romanian labour forms 20% of available labour. We have assisted workers in achieving UK settled status.
Timber & sheet materials |  | Timber Connection | Europe | Import Hardwood and clear grade of softwood (Beeach and Oak). | 4 months of stock in Nov/Dec to cover initial delays | 3 | If in stock 48-72 hours | A | If £ weakens will cost more but again if pound straengthns will cost less. They do not expect any delays due to Stockholding and they can pick which port they use. | Reordering in february so will have 3 months to arrive based on extra 4 months stock bought in Nov/Dec.
Timber & sheet materials |  | Timber Trade Federation | UK and Import | Europe | Stocks depleted | Unknown | Long lead times on Decking and fencing, General carcassing, structuralplywood, OSB and engineered wood | A | Significant impact of Covid. Sea freight and can use lots of ports but supply risk as demand higher in the US. | Must use longer term purchasing strategies to secure material. Highest Brexit risk is JIT nature of CLT and Glulam. Early arrival and storage suggested.
Timber & sheet materials |  | Arnold Laver | UK distributer | 60% outside UK of softwood, Hardwood, Plywood, Oriented Strand Board, Medium Density Fibreboard, Chipboard, Doors and Laminates. | 10-12 weeks of stock | Unknown | Extended lead timesstruggling with supply chain | A | Experiencing increase in cost and delays and availability | Regular communication is essentialto estimate demand and forward forecasr to smooth the supply chain.
Timber Trusses |  | Crendon Timber Engineering | UK and Import | Timber | 4 weeks stock in the UK | No change |  | A | Timber has increased and metal surcharge
Timber Trusses |  | Donaldson Timber Engineering | Import | Timber | 2-3 months stock | 14 | No change to lead time | A | Timber prices and transportation costs increased
Timber Trusses |  | Pasquills | UK |  |  | 14 | No change to lead time | A | Timber price increasing since Q4 2020 and increases for the forseeable future
Transformers |  | UP Systems Ltd | UAE Saudi Arabia | UAE and Saudi Arabia | 30% increase in stock | No change |  | G | Our goods are not impacted. | Brexit will not have an impact upon UP Systems so not mitigation plan required.
Transformers |  | GBE UK | Italy | Italy | 25% increase in stock | Unknown | Only delays in trucks going through Calais to Uk. No delays on materials to manufacture in Italy. | G | WTO already allows import of transformers up to 10 Mva so no issue. At worst it is a 3% import duty which will stand until GBE can clarify the new trade rules. | Yes, the only issue GBE are expecting is import duty. Which they are working alongside their hauliers to manage.
Transformers |  | FT Transformers | Italy France | Italy and France | No increase in stockholding | Unknown |  | G |  | The only potential issue FT Transformers see arising is any potential delay of materials coming through the UK ports, which as mentioned above they would then revert to UK suppliers for the goods if required to do so.
Tube & Fittings (steel, stainless steel & copper) |  | Pegler Yorkshire | France Hungary The Netherlands | Hungary and China | 10% increase in stock | Unknown |  | G | Aware of economic and tarriff rates and impact. | Strategic stock in euro warehouses from group. Dual source options available. New large stocks now available in UK.
Tube & Fittings (steel, stainless steel & copper) |  | Tata Steel Ltd | UK |  | No increase in stockholding | Unknown |  | G | As a fully integrated UK based manufacturer there is no impact to the products we supply to the UK market. | Not applicable to Tata Steel UK as a fully integrated UK based manufacturer.
Typical mid range pods |  | Elements Europe Limited | Spain Italy Germany Turkey | Spain, Italy, Germany and Turkey | 20% increase in stock | 14 | Increase on current lead times | G | No real impact expected, planning in place. | Plans in place, Stockholding where required and communication with client and supply chain.
Typical mid range pods |  | Offsite Solutions Limited | Spain, Germany, Ukraine, Bulgaria, Czech Republic, China, Italy and Portugal |  | 10% increase in stock | 14 | Increase on current lead times | G | Some delays up to 2 weeks. Cost increases in Copper 15% Steel 44% Polyster resins extra £200/t Timber 15% ( Although not impacted yet as stock levels being used. | Agreed planning with supply chain
Typical mid range pods |  | Modular Solutions Ltd | UK | Italy, Portugal, Spain, Turkey, UAE and Germany | No increase in stockholding | Unknown |  | G | Limited impact anticipated | Planning in initial stages.
Valves |  | Crane Fluid Systems | China Italy | China, Italy, France and India | 8% increase in stock | 14 | Increase on current lead times | G | Impact costed | Yes
White goods |  | Summary | UK EU Rest of World | Majority of components outside UK | Stock levels have been depleted post Covid | Unknown |  | G
Windows |  | Carey Glass | Ireland | UK and Europe | Increased stocks over the past year due to 2 out of 3 float manufacturers going offline for 4-6 months. Perceived as bigger risk than Brexit. | No change |  | G | Worth noting that biggest risk is the float tanks going offline next year. Expecting greater currency stability than have experienced over the last few years. | Extra shipments being made to Carey Glass Chester up to the end of the year.
Windows |  | AGC | Belgium France Germany Spain Czech Republic Russia | 100% Continental Europe | Increased warehouse stock capacity in the UK | Unknown | Expect longer delivery times | G | If no deal price increase of tariff and currency fluctuations.
Windows |  | Saint Gobain Glass | UK France Germany Poland | Most raw materials UK 86% reat is brought from France Geramny, Spain and Belgium | Increased critical raw materials. | Unknown |  | G | Road transport costs expected to increase. Possible currency fluctuation howver have fixed exchange rate in 2021 budget. | Moved majority to sea freight.